## Sheet1
Member | Day | Date | Time | Hours | Code | Description
Sprint-001
Laura | Monday | 2016-01-18 | 9:00am - 11:00am | 2 | LRN | TP Lab - Module outline, overview and structure
Eiren | Monday | 2016-01-18 | 9:00am - 11:00am | 2 | LRN | TP Lab - Module outline, overview and structure
Laura | Monday | 2016-01-18 | 4:00pm - 10:00pm | 6 | LRN | Testing Ketai Library, Using Android Mode (Processing)
Eiren | Monday | 2016-01-18 | 4:00pm - 10:00pm | 6 | LRN | Testing Ketai Library, Using Android Mode (Processing)
Laura | Tuesday | 2016-01-19 | 9:00am - 11:00am | 2 | PLN | TP Lab - Logo Sketches, Journal outline
Eiren | Tuesday | 2016-01-19 | 9:00am - 11:00am | 2 | LRN | TP Lab - Journal outline
Eiren | Wednesday | 2016-01-20 | 9:00am - 11:00am | 2 | GDN | Developing the different logos designed by Laura
Laura | Thursday | 2016-01-21 | 12:00pm - 5:15pm | 5.25 | PLN | Version specification, release schedule, create planning document
Eiren | Thursday | 2016-01-21 | 12:00pm - 5:15pm | 5.25 | PLN | Version specification, release schedule, create planning document
Eiren | Friday | 2016-01-20 | 10.00am - 11.00am | 1 | DOC | User Stories
Laura | Saturday | 2016-01-23 | 3:00pm - 7:00pm | 4 | PLN | Creating Management of Multimedia Project document, creating 2 x user stories, testing export APK and upload to Google Play Store
Eiren | Saturday | 2016-01-23 | 3.00pm - 5.45pm | 2.75 | PLN | Updating Trello, App Specification
Laura | Sunday | 2016-01-24 | 6:00pm - 7:30pm | 1.5 | PLN | Updating GanttPro, creating Rate Card
Eiren | Sunday | 2016-01-24 | 9.00pm - 1.30am | 4.5 | DOC | Creating Effective Teamwork document, team charter, revisit of user stories
Laura | Monday | 2016-01-25 | 9:00am - 11:00am | 2 | LRN | TP Lab - Review Journals, documentation and discussing GitHub branches with John
Eiren | Monday | 2016-01-25 | 9:00am - 11:00am | 2 | LRN | TP Lab - Review Journals, documentation and discussing GitHub branches with John
Laura | Monday | 2016-01-25 | 2:30pm - 5:00pm | 2.5 | PLN | Team Meeting - Reviewed latest version of the app, revised sprint backlog, reviewed Sprint-001, Reorganised GitHub and Google Drive
Eiren | Monday | 2016-01-25 | 2:30pm - 5:00pm | 2.5 | PLN | Team Meeting - Reviewed latest version of the app, revised sprint backlog, reviewed Sprint-001, Reorganised GitHub and Google Drive
Laura | Monday | 2016-01-25 | 5:30pm - 6:30pm | 1 | PLN | Reconfiguring GanttPro (all sprints now self contained within one parent element)
Eiren | Monday | 2016-01-25 | 5.30pm - 8.30pm | 3 | DOC | Effective teamwork document
Total hours for Sprint-001 |  |  | 59.25
Sprint-002
Laura | Tuesday | 2016-01-26 | 9:00am - 11:00 am | 2 | PLN | TP Lab, review planning documentation with John, trello changes, Management of DM documentation
Eiren | Tuesday | 2016-01-26 | 9:00am - 11:00 am | 2 | PLN | TP Lab, review planning documentation with John, trello changes, Effective Teamwork document
Eiren | Tuesday | 2016-01-26 | 8:00pm - 9.00pm | 1 | PLN | Update of trello content - input of dates and sprint cycle cards
Laura | Wednesday | 2016-01-27 | 11:00am - 1:30pm | 2.5 | RES | Management of DM (Project scope, copyright issues), research of Google API costs, limitations, privacy and content policies
Laura | Wednesday | 2016-01-27 | 7:30pm - 10:30pm | 3 | DOC | Management of DM (legal and copyright issues), research of Twitter4J, Ketai, Processing, Twitter4J and GitHub terms of use (and assoicated charges)
Laura | Thursday | 2016-01-28 | 2:30pm - 10:00pm | 7.5 | PLN | Wireframing app
Eiren | Thursday | 2016-01-28 | 2:30pm - 10:00pm | 7.5 | PLN | Wireframing app
Laura | Friday | 2016-01-29 | 6:00pm - 7:00pm | 1 | LRN | Watching Lynda.com (GitHub for Web Designers)
Laura | Friday | 2016-01-29 | 7:30pm - 8:00pm | 0.5 | DOC | Scanning in wireframes from sprint-02
Laura | Friday | 2016-01-29 | 9:00pm - 3:30am | 6.5 | LRN | Bug fixing incompatibility with Nexus, trying to access frontfacing camera
Laura | Saturday | 2016-01-30 | 1:30pm - 3:30pm | 2 | TST | Remote testing of switching cameras (over the phone)
Eiren | Saturday | 2016-01-30 | 1:30pm - 3:30pm | 2 | TST | Remote testing of switching cameras (over the phone)
Laura | Saturday | 2016-01-30 | 3:30pm - 6:00pm | 2.5 | LRN | Experimenting with device orientation and flipping the image when using the front facing camera
Eiren | Saturday | 2016-01-30 | 6.00pm - 9.00pm | 3 | DEV | Coding saving images to device, currently not fully working
Eiren | Saturday | 2016-01-30 | 9.30pm - 10.30pm | 1 | LRN | Watching Lynda.com (GitHub for Web Designers)
Laura | Sunday | 2016-01-31 | 8:00pm - 9:45pm | 1.75 | LRN | Revising Lynda.com GitHub for Web Designers
Eiren | Sunday | 2016-01-31 | 5:00pm - 8:00pm | 3 | DEV | Storing Image on device
Eiren | Sunday | 2016-01-31 | 10.30pm - 11.30pm | 1 | DOC | Refining Effective Teamwork Document - Belbin, Kilmann, SWOT, team development
Laura | Monday | 2016-02-01 | 4:45am - 6:30am | 1.75 | DOC | Management Document - Change and risk management plans, along with accompanying forms and logs
Eiren | Sunday | 2016-01-30 | 11.30pm - 2:00am | 2.5 | DEV | Storing Image on device
Eiren | Monday | 2016-02-01 | 7.30am - 9.00am | 1.5 | PLN | Re-drawing of wireframes
Laura | Monday | 2016-02-01 | 7.30am - 9.00am | 1.5 | PLN | Re-drawing of wireframes
Laura | Monday | 2016-02-01 | 9:00am - 11:00am | 2 | PLN | Finalising wireframe-02-008, review with John, experimenting with Balsamiq
Eiren | Monday | 2016-02-01 | 9:00am - 11:00am | 2 | PLN | Finalising wireframe-02-008, review with John, experimenting with Balsamiq
Eiren | Monday | 2016-02-01 | 11.00am - 12.00am | 1 | PLN | Digital Wireframing (mybalsamiq.com)
Laura | Monday | 2016-02-01 | 11.00am - 12.00am | 1 | PLN | Digital Wireframing (mybalsamiq.com)
Eiren | Monday | 2016-02-01 | 3:15pm - 8:00pm | 4.75 | PLN | Camera switch fix, planning for sprint-03, Wireframe prototype completed
Laura | Monday | 2016-02-01 | 3:15pm - 8:00pm | 4.75 | PLN | Camera switch fix, planning for sprint-03, Wireframe prototype completed
Eiren | Monday | 2016-02-01 | 10:30pm - 11:30pm | 1 | DOC | Compiling the Planning Document (Management, Effective Teamwork, App Specifications, User Stories)
Total hours for Sprint-002 |  |  | 73.5
Sprint-003
Laura | Tuesday | 2016-02-02 | 9:00am - 11:00am | 2 | DOC | Completing Management of DM (Myers Briggs)
Eiren | Tuesday | 2016-02-02 | 9:00am - 11:00am | 2 | DOC | Compiling of planning documents
Eiren | Tuesday | 2016-02-02 | 4:30pm - 6.30pm | 2 | GDN | Creation of graphics for app
Eiren | Tuesday | 2016-02-02 | 7:30pm - 8:30pm | 1 | GDN | Creation of graphics for app
Eiren | Tuesday | 2016-02-02 | 10:00pm - 12:30am | 2.5 | LRN | Learnng more about saving an image
Laura | Wednesday | 2016-02-03 | 1:30pm - 9:15pm | 7.75 | DEV | Beginning building the basic structure of the app
Eiren | Wednesday | 2016-02-03 | 3:00pm - 7:00pm | 4 | DEV | Trying to save image
Laura | Thursday | 2016-02-04 | 2:00pm - 4:15pm | 2.25 | DEV | Working on making app structure responsive
Eiren | Thursday | 2016-02-04 | 7:00pm - 7:45pm | 0.75 | TST | testing saving images
Laura | Friday | 2016-02-05 | 12:00pm - 2:00pm | 2 | DEV | Streamlining switching of pages, adding consistency to icons positions
Eiren | Friday | 2016-02-05 | 4:00pm - 7:30pm | 3.5 | PLN | Design Justifications
Laura | Friday | 2016-02-05 | 4:00pm - 8:00pm | 4 | PLN | Design Justifications
Eiren | Saturday | 2016-02-06 | 7:00pm - 12:00am | 5 | DOC | Compiling Planning Documentation and formatting, addition of bibliography, references and appendix
Eiren | Saturday | 2016-02-06 | 3:00pm - 4:00pm | 1 | LRN | Learning about saving
Eiren | Saturday | 2016-02-06 | 2:00pm - 8:30pm | 6.5 | DEV | Created a save directory in the pictures folder, saving an image
Laura | Sunday | 2016-02-07 | 3:30pm - 6:30pm | 3 | DEV | Refining basic layout (switchScreens(), addText() and addImage()). Adding ImagePreviewScreen, SaveShareScreenA, SaveShareScreenB, SharingScreen, ShareSuccessfulScreen and ShareUnsuccessfulScreen
Eiren | Sunday | 2016-02-07 | 7:30pm - 8:15pm | 0.75 | PLN | Phone call on project progression and discussion on current code progress
Laura | Sunday | 2016-02-07 | 7:30pm - 8:15pm | 0.75 | PLN | Phone call on project progression and discussion on current code progress
Eiren | Sunday | 2016-02-07 | 8:30pm - 8:45pm | 0.25 | TST | Re-testing code for saving an image
Laura | Sunday | 2016-02-07 | 9:30pm - 12:30am | 3 | DEV | Added last of the screens, reconfigured for background images, final linkage of all screens
Laura | Monday | 2016-02-08 | 1:00am - 1:30am | 0.5 | TST | Testing on Nexus, change back to if/else instead of switch statement (incompatibility with Android)
Eiren | Monday | 2016-02-08 | 07:00am - 8:30am | 1.5 | GDN | Created the home, switch camera, facebook, tick, X, save and delete icons
Eiren | Monday | 2016-02-08 | 9:00am - 11:45am | 2.75 | DEV | Compiling the basic app layout with the camera (switching between views)
Laura | Monday | 2016-02-08 | 9:00am - 11:45am | 2.75 | DEV | Compiling the basic app layout with the camera (switching between views)
Eiren | Monday | 2016-02-08 | 2:30pm - 7:15pm | 4.75 | DEV | Compiling code into main app - save image to device
Laura | Monday | 2016-02-08 | 2:30pm - 9:15pm | 6.75 | DEV | Exporting app graphics, compiling saving images code and interface graphics into main app
Total hours for Sprint-003 |  |  | 73
Sprint-004
Laura | Tuesday | 2016-02-09 | 9:00am - 11:00am | 2 | PLN | Planning for Sprint-04, Reviewing progress with John
Eiren | Tuesday | 2016-02-09 | 9:00am - 11:00am | 2 | PLN | Planning for Sprint-04, Reviewing progress with John
Eiren | Wednesday | 2016-02-09 | 6:30pm - 7:30pm | 1 | GDN | Social Media Icons - Facebook, Email, Instagram
Eiren | Thursday | 2016-02-10 | 7:00am - 8:30am | 1.5 | GDN | Twiter, Accelerometer icon, retry, cancel, completed favourites background
Laura | Thursday | 2016-02-11 | 2:00pm - 5:30pm | 3.5 | DOC | Wrote about user stories, design justication, app specifications, scheduled release plan, wireframes, prototypes
Eiren | Thursday | 2016-02-11 | 2:00pm - 5:30pm | 3.5 | DOC | Wrote about user stories, design justication, app specifications, scheduled release plan, wireframes, prototypes
Laura | Thursday | 2016-02-11 | 5:30pm - 8:30pm | 3 | DEV | Pair programming - saving image to device
Eiren | Thursday | 2016-02-11 | 5:30pm - 8:30pm | 3 | DEV | Pair programming - saving image to device
Eiren | Friday | 2016-02-12 | 2:00pm - 4:30pm | 2.5 | DOC | Re-ordering sections, transfered into MS Word, Applied formatting such as headers and footer, put in cover and contents page.
Laura | Friday | 2016-02-12 | 6:00pm - 10:00pm | 4 | LRN/DEV | Reassessing the current layout of the app's structure
Eiren | Satuday | 2016-02-13 | 3:15pm - 4:30pm | 1.25 | DOC | Formatting and inclusion of PDF prototype and gradable project into doc and cover images
Eiren | Saturday | 2016-02-13 | 8:00pm - 8:30am | 3 | LRN | Learning and implementing text input on Java mode
Eiren | Saturday | 2016-02-13 | 8:30pm - 11:00am | 3 | DEV | Learning and implementing text input on Java mode
Laura | Saturday | 2016-02-13 | 9:00am - 12:00pm | 3 | DEV | Seperating Icons and Buttons to be two seperate classes, which extend from a "Clickable Element" class
Eiren | Sunday | 2016-02-14 | 2:00pm - 4:45pm | 2.75 | LRN | Learning aout text input fields
Laura | Sunday | 2016-02-14 | 4:30pm - 10:00pm | 5.5 | DEV | Stopping progress on icon/Buttons (due to previous Screen array issue), continuing on with refining layout, creating scrollable screen (About Screen), allowing icons to specify if text should appear on them or below them, creating external hyperlinks (i.e. for social media links)
Eiren | Sunday | 2016-02-14 | 9:00pm - 11:00pm | 2 | DEV | Text Input using Control p5 library for textfields
Laura | Sunday | 2016-02-14 | 11:15pm - 12:00am | 0.75 | DEV | Fixed scrolling on About page
Eiren | Monday | 2016-02-15 | 11:00am - 11:30am | 0.5 | GDN | Saved and completed last graphic - about background, uploaded all images for the app with naming conventions
Eiren | Monday | 2016-02-15 | 11:45am - 12:30pm | 0.75 | DEV | Getting text input to work on android device
Eiren | Monday | 2016-02-15 | 12:30pm - 1:30pm | 1 | PLN | Phone call on how to fix save image and discussion on presentation
Laura | Monday | 2016-02-15 | 12:30pm - 1:30pm | 1 | PLN | Phone call on how to fix save image and discussion on presentation
Laura | Monday | 2016-02-15 | 2:15pm - 6:00pm | 3.75 | DEV | fixing corrupted branch, Finalizing Text input
Eiren | Monday | 2016-02-15 | 2:15pm - 6:00pm | 3.75 | DEV | fixing corrupted branch, Finalizing Text input
Laura | Monday | 2016-02-15 | 7:00pm - 10:00pm | 3 | DEV | Trying to solve saving an image after preview screen, Also completed planning for this sprint
Eiren | Monday | 2016-02-15 | 7:00pm - 10:00pm | 3 | DEV | Trying to solve saving an image after preview screen, Also completed planning for this sprint
Total hours for Sprint-004 |  |  | 64
Sprint-005
Eiren | Tuesday | 2016-02-16 | 11:15am - 12:45pm | 1.5 | DEV | Working with John trying to solve saving an image
Laura | Tuesday | 2016-02-16 | 11:15am - 12:45pm | 1.5 | DEV | Working with John trying to solve saving an image
Laura | Tuesday | 2016-02-16 | 7:00pm - 7:15pm | 0.25 | PLN | Phone call to discuss plans for this evening's meeting
Eiren | Tuesday | 2016-02-16 | 7:00pm - 7:15pm | 0.25 | PLN | Phone call to discuss plans for this evening's meeting
Laura | Tuesday | 2016-02-16 | 7:45pm - 9:00pm | 1.25 | DEV | Incorporating saving of image into the main sketch
Eiren | Tuesday | 2016-02-16 | 7:45pm - 9:00pm | 1.25 | DEV | Incorporating saving of image into the main sketch
Laura | Tuesday | 2016-02-16 | 9:00pm - 9:45pm | 0.75 | DEV | Incorporating textInput into the main sketch
Eiren | Tueday | 2016-02-16 | 9:15pm - 1:45AM | 4.5 | DOC | Finalizing Planning document
Laura | Tuesday | 2016-02-16 | 11:45pm - 2:30am | 2.75 | DEV | TextInput fields trigger keyboard, creating all text inputs, restraining textInputs to a text box, refining alignment
Laura | Wednesday | 2016-02-17 | 10:15am - 12:15pm | 2 | DOC | Wrote about prototype testing, inserted belbin team chart, inserted images from promotional presentation, created basis of invoice, logged Laura's hours for invoice, talked with John re Nexus not running sketch on his laptop
Eiren | Wednesday | 2016-02-17 | 10:15am - 12:15pm | 2 | DOC | Wrote about prototype testing, inserted belbin team chart, inserted images from promotional presentation, created basis of invoice, logged Laura's hours for invoice, talked with John re Nexus not running sketch on his laptop
Laura | Wednesday | 2016-02-17 | 6:00pm - 6:15pm | 0.25 | DEV | Final testing and release of Sprint-04-Alpha-09 on Google Play
Laura | Wednesday | 2016-02-17 | 6:15pm - 7:00pm | 0.75 | PLN | Creating outline of progress presentation for next week
Eiren | Wednesday | 2016-02-17 | 6:15pm - 7:00pm | 0.75 | PLN | Creating outline of progress presentation for next week
Eiren | Wednesday | 2016-02-17 | 10:00pm - 11:00pm | 1 | LRN | Learning about twitter
Laura | Friday | 2016-02-19 | 5:00pm - 8:30pm | 3.5 | PLN | Finalising the planning documentation, finalising the presentation PowerPoint, printing the planning documentation
Eiren | Friday | 2016-02-19 | 5:00pm - 8:30pm | 3.5 | PLN | Finalising the planning documentation, finalising the presentation PowerPoint, printing the planning documentation
Eiren | Saturday | 2016-02-20 | 11:00am - 2:00pm | 3 | LRN | Twitter oAuth and Twitter4j
Laura | Saturday | 2016-02-20 | 3:15pm - 5:15pm | 2 | DEV | Green screen keying
Laura | Saturday | 2016-02-20 | 6:00pm - 8:00pm | 2 | DEV | Green screen keying - testing and refinining
Eiren | Saturday | 2016-02-20 | 6:00pm - 6.30am | 0.5 | TST | Testing Twitter
Eiren | Saturday | 2016-02-20 | 9.15pm - 10.15am | 1 | LRN | Twitter4j - Twitter login / tweeting
Eiren | Saturday | 2016-02-20 | 10.15pm - 12.00am | 1.75 | DEV | /3
Laura | Saturday | 2016-02-20 | 9:30pm - 1:45am | 4.25 | DEV | Incorporating green screen keying into main sketch
Eiren | Sunday | 2016-02-21 | 12:00pm - 1:15pm | 1.25 | DEV | Twitter login
Eiren | Sunday | 2016-02-21 | 2:45pm - 4:00pm | 1.25 | DEV | Twitter login
Laura | Sunday | 2016-02-21 | 4:00pm - 4:15pm | 0.25 | PLN | Discussing GitHub, reviewing progress made over weekend, needed to upload a file for testing so will ring back once it is online
Eiren | Sunday | 2016-02-21 | 4:00pm - 4:15pm | 0.25 | PLN | Discussing GitHub, reviewing progress made over weekend, needed to upload a file for testing so will ring back once it is online
Laura | Sunday | 2016-02-21 | 5:15pm - 5:30pm | 0.25 | TST | Tested green screen app on android phone, not working
Eiren | Sunday | 2016-02-21 | 5:15pm - 5:30pm | 0.25 | TST | Tested green screen app on android phone, not working
Laura | Sunday | 2016-02-21 | 7:15pm - 11:30pm | 4.25 | DEV | Refining alignment of app, adding images and content, returnTo, toggle favourite, favourite screen generate and scroll, adding text etc to unsuccessfull share/save/search pages
Eiren | Sunday | 2016-02-21 | 8:15pm - 12:15am | 5 | DEV | Twitter Login
Eiren | Monday | 2016-02-22 | 7:30am - 8:30am | 1 | DEV | Twitter4j Login
Laura | Monday | 2016-02-22 | 8:30am - 11:00am | 2.5 | PLN | Pair programming twitter4J login, testing green screen (working!!), reviewing all sprint tasks (need to do, nice to do), reviewed progress with John
Eiren | Monday | 2016-02-22 | 8:30am - 11:00am | 2.5 | DEV | Pair programming twitter4J login, testing green screen (working!!), reviewing all sprint tasks (need to do, nice to do), reviewed progress with John
Laura | Monday | 2016-02-22 | 2:30pm - 6:00pm | 3.5 | DEV | Optimising Greenscreen
Eiren | Monday | 2016-02-22 | 2:30pm - 6:00pm | 3.5 | DEV | Twitter login for users
Laura | Monday | 2016-02-22 | 6:00pm - 6:15pm | 0.25 | TST | Testing the incorporation of green screen keying in A106. It works kind of :)
Eiren | Monday | 2016-02-22 | 6:00pm - 6:15pm | 0.25 | TST | Testing the incorporation of green screen keying in A106. It works kind of :)
Laura | Monday | 2016-02-22 | 6:15pm - 7:00pm | 0.75 | PLN | Binding the final planning documentation, reviewing sprint-05 and planning for sprint-06
Eiren | Monday | 2016-02-22 | 6:15pm - 7:00pm | 0.75 | PLN | Binding the final planning documentation, reviewing sprint-05 and planning for sprint-06
Total hours for Sprint-005 |  |  | 70
Sprint-006
Laura | Monday | 2016-02-22 | 7:00pm - 8:45pm | 1.75 | GDN | Creating additional graphics for app
Eiren | Monday | 2016-02-22 | 7:00pm - 8:45pm | 1.75 | DEV | Creating toggle switches for settings page, incorporating in new graphics in app
Laura | Monday | 2016-02-22 | 11:30pm - 12:30am | 1 | PLN | Exporting APKs for the demonstration tomorrow
Laura | Tuesday | 2016-02-23 | 8:15am - 9:00am | 0.75 | PLN | Preparation for presentation, gathering of final materials
Eiren | Tuesday | 2016-02-23 | 7:00am - 9:00am | 2 | PLN | Preparation for presentation, gathering of final materials
Laura | Tuesday | 2016-02-23 | 9:00am - 11:00am | 2 | LRN | Presentation
Eiren | Tuesday | 2016-02-23 | 9:00am - 11:00am | 2 | LRN | Presentation
Laura | Thursday | 2016-02-25 | 2:15pm - 5:15pm | 3 | DEV | Finalising encorporation of tweeting into the app, release of Sprint-005-Alpha-10, review of acceptance tests for this week's sprint
Eiren | Thursday | 2016-02-25 | 2:15pm - 5:15pm | 3 | DEV | Finalising encorporation of tweeting into the app, release of Sprint-005-Alpha-10, review of acceptance tests for this week's sprint
Laura | Thursday | 2016-02-25 | 5:30pm - 6:00pm | 0.5 | PLN | Looking into how to go about saving the images as composite images
Eiren | Friday | 2016-02-26 | 4:00pm - 7:00pm | 3 | DEV | Sending Images and text via twitter
Eiren | Friday | 2016-02-26 | 9:00pm - 12:00am | 3 | DEV | Sending Images and text via twitter and user authorization
Laura | Friday | 2016-02-26 | 1:00pm - 10:00pm | 9 | LRN | Trying to access Google Maps API
Eiren | Sunday | 2016-02-28 | 1:00pm - 3:45pm | 2.75 | DEV | Twitter User authorization
Eiren | Sunday | 2016-02-28 | 4:15pm - 4:45pm | 0.5 | PLN | Discussion on Google Street View API
Laura | Sunday | 2016-02-28 | 4:15pm - 4:45pm | 0.5 | PLN | Discussion on Google Street View API
Laura | Sunday | 2016-02-28 | 5:00pm - 7:00pm | 2 | DEV | Using the Google Street View Image API to add a list of favourite locations to the background of the camera live view screen. Picking a random one of these locations everytime the "Random" icon is selected from the home screen
Eiren | Sunday | 2016-02-28 | 6:00pm - 9:30pm | 3.5 | DEV | Twitter User authorization
Laura | Sunday | 2016-02-28 | 7:45pm - 9:45pm | 2 | DEV | Compiling the background image, keyed image and overaly into one graphic, which will now be the one that we save out to the device
Eiren | Sunday | 2016-02-28 | 10:30pm - 11:00pm | 0.5 | PLN | Discussion on Twitter Authorization
Laura | Sunday | 2016-02-28 | 10:30pm - 11:00pm | 0.5 | PLN | Discussion on Twitter Authorization
Eiren | Monday | 2016-02-29 | 7:00am - 9:00am | 2 | DEV | Trying to save a tweet temporarily, store it and then tweet it, before final saving of the image - users choice
Laura | Monday | 2016-02-29 | 8:30am - 9:00am | 0.5 | DEV | Trying to save a tweet temporarily, store it and then tweet it, before final saving of the image - users choice
Eiren | Monday | 2016-02-29 | 9:00am - 11:00am | 2 | DEV | Looked at twitter user login authorization, discussed with John about Google Map API
Laura | Monday | 2016-02-29 | 9:00am - 11:00am | 2 | DEV | Looked at twitter user login authorization, discussed with John about Google Map API
Eiren | Monday | 2016-02-29 | 11:15am - 12:00pm | 0.75 | PLN | Planned for Sprint 07, assigned weeks tasks
Laura | Monday | 2016-02-29 | 11:15am - 12:00pm | 0.75 | PLN | Planned for Sprint 07, assigned weeks tasks
Laura | Monday | 2016-02-29 | 3:00pm - 3:30pm | 0.5 | DEV | Fixing scrolling on FavouritesScreen. Compiling & releasing Sprint-006-Alpha-11-Release
Total hours for Sprint-006 |  |  | 53.5
Sprint-007
Laura | Tuesday | 2016-03-01 | 9:30am - 11:30am | 2 | PLN | Updating GanttPro, installing Android Studio and Java Development Kit, reviewing project plan, installing Android Studio and Java Development Environment
Eiren | Tuesday | 2016-03-01 | 9:30am - 11:00am | 1.5 | DEV | Twitter Authorization, reviewing project plan
Laura | Tuesday | 2016-03-01 | 5:15pm - 6:15pm | 1 | DEV | Experimenting with Android Studio. Loading in a static Google Map
Laura | Tuesday | 2016-03-01 | 7:30pm - 11:45pm | 4.25 | DEV | Experimenting with Android Studio. Successfully generating an interactive Google Street View panorama. Accessing and altering the settings of the panorama, as well as the panorama camera.
Laura | Thursday | 2016-03-03 | 2:45pm - 4:45pm | 2 | DEV | Trying to access Twitter login through Twitter4J. Adding an intent-filter to AndroidManifest.xml to try and get the user to be brought back to the app after authorisation
Eiren | Thursday | 2016-03-03 | 2:45pm - 4:45pm | 2 | DEV | Trying to access Twitter login through Twitter4J.
Laura | Thursday | 2016-03-03 | 7:15pm - 9.45pm | 2.5 | DEV | Testing previous intent filter (resetting app). Experimenting with logging into Twitter using Android Studio and Fabric
Eiren | Saturday | 2016-03-05 | 2:00pm - 5:00pm | 3 | DEV | Re-install of Android Studio and SDK, Trying to get Twitter login to work using Fabric
Eiren | Saturday | 2016-03-05 | 7:30pm - 10:30pm | 3 | DEV | Re-install of Android Studio and SDK, Trying to get Twitter login to work using Fabric
Laura | Saturday | 2016-03-05 | 8:00pm - 1:45am | 5.75 | DEV | Looking at ways to search for locations, allowing user to imitate an interactive image, incorporating searching for locations and imitate interactive images into main app
Laura | Sunday | 2016-03-06 | 2:00pm - 5:00pm | 3 | DEV | Refining movement of interactive images, restraining min/max. Getting name of current location (placing it on the screen temporarily)
Laura | Sunday | 2016-03-06 | 7:30pm - 9:30pm | 2 | LRN | Watching Android App Development Essential Training on Lynda.com (http://www.lynda.com/Android-tutorials/Android-App-Development-Essential-Training/442863-2.html)
Eiren | Sunday | 2016-03-06 | 6:00pm - 9:00pm | 3 | DEV | Twitter User Login
Eiren | Monday | 2016-03-07 | 7:30am - 8:30am | 1 | DEV | Trying to get Twitter User login to work
Laura | Monday | 2016-03-07 | 9:00am - 11:45am | 2.75 | PLN | Reviewing issue with Twitter login with John, testing "interactive" street view images in processing, reversing the movements required to move around the image, trying to create a new activity in Processing
Eiren | Monday | 2016-03-07 | 9:00am - 11:00am | 2 | PLN | Reviewing issue with Twitter login with John, testing "interactive" street view images in processing, reversing the movements required to move around the image
Eiren | Monday | 2016-03-07 | 3:15pm - 6:00pm | 2.75 | DEV | Trying to get a processing sketch running in Android Studio, looked at resources such as: https://github.com/processing/processing-android/wiki/Using-Eclipse-or-Android-Studio-for-Development
Laura | Monday | 2016-03-07 | 3:15pm - 4:45pm | 1.5 | DEV | Trying to get a processing sketch running in Android Studio using a tutorial on http://andymodlaphotography.blogspot.ie/2015/07/processing-sketches-using-android-studio.html
Laura | Monday | 2016-03-07 | 7:15pm - 10:00pm | 2.75 | DEV | Using Temboo to authorise Twitter users (https://temboo.com/library/Library/Twitter/OAuth/) - works on PC, still doesn't redirect on Android
Eiren | Monday | 2016-03-07 | 7:30pm - 9:00pm | 1.5 | DOC | Drawing up the change request forms for potiental change in the project
Eiren | Monday | 2016-03-07 | 9:30pm - 12:30pm | 3 | DEV | Writing code for accessing the last saved image / researching caching an image n internal storage for twitter tweeting
Laura | Monday | 2016-03-07 | 11:00pm - 6:15am | 7.25 | DEV | Attempting to write an activity in Processing, trying to replicate the tutorial I was working on earlier today, successfully running a Processing Sketch in Android Processing, getting the Twitter Login app for Android Studio to display the username of the account that has just logged in (testing purposes)
Eiren | Tuesday | 2016-03-08 | 7:00am - 11:30am | 4.5 | DEV | Ability to access last image saved and sharing it on the @WishIWasHere account, incorporating it into a processing prototype and then incorporating it into the main sketch, Change Request Review Board
Laura | Tuesday | 2016-03-08 | 7:30am - 8:30am | 1 | TST | Testing the latest version of the app on Eiren's phone, making minor fixes, releasing version 7.0 of the app on Google Play
Laura | Tuesday | 2016-03-08 | 9:00am - 11:30am | 2.5 | DEV | Working on tweeting images out to Twitter, fixing switching between screens, releasing version 7.1 of the app on Google Play, planning for sprint-008, Change Request Review Board
Total hours for Sprint-007 |  |  | 67.5
Sprint-008
Laura | Thursday | 2016-03-10 | 2:45pm - 5:45pm | 3 | DEV | Restricting text input to text boxes
Eiren | Thursday | 2016-03-10 | 2:45pm - 5:45pm | 3 | DEV | Restricting text input to text boxes
Eiren | Thursday | 2016-03-10 | 7.45pm - 8:15pm | 0.5 | GDN | Re-doing Overlay and sizing searching Image
Eiren | Thursday | 2016-03-10 | 8:30pm - 8.45pm | 0.25 | DEV | Incorporation of new graphics into code
Laura | Thursday | 2016-03-10 | 9:00pm - 2:00am | 5 | LRN | Trying to figure out how to replicate the Processing in Android work I had completed on Monday night - not working
Laura | Friday | 2016-03-11 | 3:00pm - 6:45pm | 3.75 | LRN | Trying to figure out how to replicate the Processing in Android work I had completed on Monday night - finally working (wrong Processing library)
Eiren | Friday | 2016-03-11 | 7:00pm - 8:30pm | 1.5 | LRN | Twitter Login in android studio, tried a tutorial but still doesnt fully work
Eiren | Friday | 2016-03-11 | 8:30pm - 11:00pm | 2.5 | DEV | Twitter Login in android studio, tried a tutorial but still doesnt fully work
Eiren | Saturday | 2016-03-12 | 9:00am - 11:15am | 2.25 | LRN | Twitter Login in android studio
Laura | Saturday | 2016-03-12 | 1:00pm - 7:15pm | 6.25 | DEV | Migrating app to Android Studio - app successfully moved over, changed all constructors to take PApplet as a parametre, and calling Processing methods from this
Eiren | Saturday | 2016-03-12 | 1:15pm - 3:30pm | 2.25 | DEV | Learning about twitter login and trying to implement it - still not working, still getting errors
Eiren | Saturday | 2016-03-12 | 4:30pm - 11:00pm | 6.5 | DEV | Twitter Login - Create a new one and went back to an old version and trying to tweak it
Laura | Saturday | 2016-03-12 | 8:00pm - 2:15am | 6.25 | DEV | Migrating app to Android Studio - issue with variable shadowing, global variables and methods are not really available (corrosponding values do not change, but locally they appear to have)
Laura | Sunday | 2016-03-13 | 3:15pm - 3:30pm | 0.25 | DEV | Fixing shadowing issue in a prototype :)
Eiren | Sunday | 2016-03-13 | 3:00pm - 8:30pm | 5.5 | DEV | Still fighting with twitter
Eiren | Sunday | 2016-03-13 | 9:00pm - 10:30pm | 1.5 | DEV | Still fighting with twitter
Laura | Sunday | 2016-03-13 | 6:00pm - 8:45pm | 2.75 | DEV | Implementing the variable shadowing fix into the main app
Laura | Sunday | 2016-03-13 | 9:45pm - 1:15am | 3.5 | DEV | Fixing ketaiCamera in Android Studio, implementing adding to favourites
Eiren | Monday | 2016-03-14 | 7:00am - 8.45am | 1.75 | DEV | Twitter login..... think im close....
Laura | Monday | 2016-03-14 | 9:00am - 11:00am | 2 | PLN | Testing Android Studio version, and adding to favourites on Eirens phone, reviewing issue with Twitter login with John, reviewing methods for passing the Sketch class
Eiren | Monday | 2016-03-14 | 9:00am - 11:00am | 2 | PLN | Testing Android Studio version, and adding to favourites on Eirens phone, reviewing issue with Twitter login with John, reviewing methods for passing the Sketch class
Laura | Monday | 2016-03-14 | 2:30pm - 4:30pm | 2 | PLN | Sprint review, acceptance tests, releasing sprint-008-alpha-14, planning for sprint-009
Eiren | Monday | 2016-03-14 | 2:30pm - 4:30pm | 2 | PLN | Sprint review, acceptance tests, releasing sprint-008-alpha-14, planning for sprint-009
Total hours for Sprint-008 |  |  | 66.25
Sprint-009
Laura | Monday | 2016-03-14 | 4:30pm - 5:30pm | 1 | DOC | Composing email to John re: using Fabric in Android Studio
Eiren | Monday | 2016-03-14 | 4:30pm - 5:30pm | 1 | DOC | Composing email to John re: using Fabric in Android Studio
Eiren | Tuesday | 2016-03-15 | 8:45am - 10:30am | 1.75 | PLN | Researching icons for potiential change in application.
Laura | Friday | 2016-03-18 | 1:00pm - 2:00pm | 1 | DEV | Successfully accessing user's Access Token and Secret Token when they log in to Twitter
Eiren | Friday | 2016-03-18 | 5:00pm - 7:30pm | 2.5 | LRN | Saving to internal storage on device
Laura | Saturday | 2016-03-19 | 5:30pm - 8:15pm | 2.75 | DEV | Trying to login to Twitter by switching activities, Integrating the Twitter login into the main app
Laura | Sunday | 2016-03-20 | 1:00am - 2:00am | 1 | DEV | Trying to fix the sketch reset issue
Laura | Sunday | 2016-03-20 | 5:00pm - 8:45pm | 3.75 | DEV | Trying to add fabric as a fragment to MainActivity
Laura | Sunday | 2016-03-20 | 8:45pm - 10:00pm | 1.25 | DEV | Reverting to using Activities to incorporate Twitter login with Processing
Eiren | Sunday | 2016-03-20 | 9:00pm - 10:00pm | 1 | DEV | Registered a new client application for instagram, basic learning on incorporating instagram into application
Eiren | Sunday | 2016-03-20 | 10:00pm - 11:00pm | 1 | TST | Testing androidStudio_20032016_a_TwitterAccess8 to see if tweet will send from users account. IT WORKS!!!!
Laura | Sunday | 2016-03-20 | 10:15pm - 11:00pm | 0.75 | TST | Testing androidStudio_20032016_a_TwitterAccess8 to see if tweet will send from users account. IT WORKS!!!!
Laura | Sunday | 2016-03-20 | 11:30pm - 12:30am | 1 | DEV | Experimenting with using Processing server-side
Eiren | Sunday | 2016-03-20 | 12:00am - 1:15am | 1.25 | DEV | Internal Storage
Laura | Monday | 2016-03-21 | 9:15am - 10:30am | 1.25 | DEV | Experimenting with processing and node.js
Laura | Monday | 2016-03-21 | 11:00am - 2:30pm | 3.5 | DEV | Experimenting with jimp and onecolor in node.js - some success
Eiren | Monday | 2016-03-21 | 7:00am - 10:30am | 3.5 | LRN | Still trying to learn/understand instagram, still not sure where to start but created an intent on an android studio file for the sending of images and text
Eiren | Monday | 2016-03-21 | 2:00pm - 4:30pm | 2.5 | DEV | Figured out how to change the app icon, applied an icon library, two versions, one black see through icons and black outlined and white fill icons
Eiren | Monday | 2016-03-21 | 5:00pm - 7:30pm | 2.5 | DEV | Still working on instagram and internal storage....
Eiren | Monday | 2016-03-21 | 9:00pm - 4:30am | 7.5 | DEV | Internal Storage, still trying to get it to work, tried different ways including for an image and creating a file and directory, switched to trying to delete a directory to act as a cache folder,
Eiren | Tuesday | 2016-03-22 | 7:15am - 8:00am | 0.75 | DEV | Deletion of a directory and its content - not working due some other erros preventing me from reaching the point where I can actually test it..
Eiren | Tuesday | 2016-03-22 | 9.15am - 1:15pm | 3 | DEV | Revision of twitter login, fixed directory - creates a new directory if it doesn't exist
Eiren | Tuesday | 2016-03-22 | 9.15am - 1:15pm | 1 | PLN | completed acceptance tests, Planning for next sprint, reviewed sprint progress
Laura | Tuesday | 2016-03-22 | 9.15am - 1:15pm | 4 | PLN/DEV | Revision of twitter login, fixed directory - creates a new directory if it doesn't exist, completed acceptance tests, Planning for next sprint, reviewed sprint progress
Eiren | Tuesday | 2016-03-22 | 2:45pm - 5:00pm | 2.25 | DOC | completed change request form
Eiren | Tuesday | 2016-03-22 | 5:00pm - 6:00pm | 1 | DEV | Releasing sprint-009-alpha-15
Laura | Tuesday | 2016-03-22 | 2:45pm - 6:00pm | 3.25 | DEV/DOC | Releasing sprint-009-alpha-15, completed change request form
Laura | Tuesday | 2016-03-22 | 10:30pm - 2:00am | 3.5 | DEV | Fixing issue with green screening on server (still slow, but accurate)
Total hours for Sprint-009 |  |  | 60.5
Sprint-010
Laura | Wednesday | 2016-03-23 | 7:30am - 2:00pm | 6.5 | DEV | Successfully storing twitter image locally before sending to twitter. Loading and saving an xml file for the favourites tabs, currently think the files are shadowing one another but just found a way to get a more direct path (sketchPath("favourite_locations.xml") I hope
Eiren | Thursday | 2016-03-24 | 2:30pm - 5:30pm | 3 | DEV | Restricting text prototypes, attempt at intergration into main processing sketch
Eiren | Thursday | 2016-03-24 | 6:00pm - 10:00pm | 4 | DEV | Creation of landing page in android studio with design, intergration of restricting text character limit into main processing sketch
Laura | Thursday | 2016-03-24 | 8:45pm - 10:00pm | 1.25 | DEV | Intergration of restricting text character limit into main processing sketch
Eiren | Friday | 2016-03-25 | 1:30am - 2:00am | 0.5 | DEV | Tweaks to main processing sketch - alignments of the sharescreenB
Eiren | Friday | 2016-03-25 | 2:15am - 3.45am | 1.5 | DEV | Intergation of main processing sketch changes into android studio
Laura | Sunday | 2016-03-27 | 3:15pm - 3:45pm | 0.5 | TST | Final testing of persisting XML across sessions in a prototype
Eiren | Monday | 2016-03-28 | 3:00pm - 4:30pm | 1.5 | LRN | Learning abot accelerometer movement
Laura | Monday | 2016-03-28 | 3:30pm - 5:00pm | 1.5 | DEV | Instagram login - getting user's access token
Laura | Monday | 2016-03-28 | 5:00pm - 6:00pm | 1 | RES | Researching how to send image to user's account
Laura | Monday | 2016-03-28 | 6:00pm - 6:45pm | 0.75 | DEV | Sending images on Instagram through intents
Laura | Monday | 2016-03-28 | 8:00pm - 9:00pm | 1 | PLN | Merging of GitHub branch, review of progress
Eiren | Monday | 2016-03-28 | 8:00pm - 9:00pm | 1 | PLN | Merging of GitHub branch, review of progress
Eiren | Monday | 2016-03-28 | 10.30pm - 4:00am | 5.5 | DEV | Refining basic accelerometer movement for our project
Eiren | Tuesday | 2016-03-29 | 7:00am - 9:30am | 1.5 | DEV | Refining basic accelerometer movement for our project
Laura | Tuesday | 2016-03-29 | 10:30am - 11:30am | 1 | PLN | Planning, discussing progress
Eiren | Tuesday | 2016-03-29 | 10:30am - 11:30am | 1 | PLN | Planning, discussing progress
Eiren | Tuesday | 2016-03-29 | 11:30am - 1:00pm | 1.5 | DEV | Accelerometer Movement
Laura | Tuesday | 2016-03-29 | 11:30am - 1:00pm | 1.5 | DEV | Integration of saving favourites into the main app
Laura | Tuesday | 2016-03-29 | 2:30pm - 3:00pm | 0.5 | DEV | Fixing of favourites, removal of camera live view title
Eiren | Tuesday | 2016-03-29 | 2:30pm - 3:00pm | 0.5 | DEV | Accelerometer Movement
Eiren | Tuesday | 2016-03-29 | 3:00pm - 3:30pm | 0.5 | DEV | Integrating of text restriction into main app
Laura | Tuesday | 2016-03-29 | 3:00pm - 3:30pm | 0.5 | DEV | Integrating of text restriction into main app
Eiren | Tuesday | 2016-03-29 | 3:30pm - 7:30pm | 4 | DEV | Accelerometre movement of image, intergration into main processing sketch prototype
Laura | Tuesday | 2016-03-29 | 3:30pm - 5:00pm | 1.5 | DEV | Integrating of saving images locally (for twitter), checking if autosave mode on, and creation of seperate save functions (one for photo gallery, one for local to the app) autosave mode on/off
Laura | Tuesday | 2016-03-29 | 5:00pm - 7:00pm | 2 | DEV | Accelerometre movement of image
Laura | Tuesday | 2016-03-29 | 7:00pm - 7:30pm | 0.5 | DEV | Storing of user preferences
Laura | Tuesday | 2016-03-29 | 7:30pm - 8:45pm | 1.25 | DEV | Planning, integrating of accelerometer image, sprint release
Eiren | Tuesday | 2016-03-29 | 7:30pm - 8:45pm | 1.25 | DEV | Planning, integrating of accelerometer image, sprint release
Total hours for Sprint-010 |  |  | 48.5
Sprint-011
Eiren | Wednesday | 2016-03-30 | 7:30am - 8:15am | 0.75 | GDN | Graphics - De-Selected Twitter, Accelerometer Off (3 versions), de-selected Save, exported these graphics, renamed them, ready for incorporation
Eiren | Wednesday | 2016-03-30 | 9:00am - 10:00am | 1 | GDN | Graphics - Team Logo PNG - resized, 3 versions mades
Eiren | Wednesday | 2016-03-30 | 10:00am - 10:15am | 0.25 | DEV | New App icon incorporated into main application
Eiren | Thursday | 2016-03-31 | 9:00am - 10:00am | 1 | DEV | Fixing / optimizing the landing page layout
Eiren | Thursday | 2016-03-31 | 10:00am - 11:15am | 1.25 | TST | Testing the new landing page layout on samsumg core prime, samsung fame and nexus. Problem with nexus, not displaying the picture but phones are.
Eiren | Thursday | 2016-03-31 | 11:30am - 12:30pm | 1 | LRN | Researching methods for detecting the orientation of the device
Eiren | Thursday | 2016-03-31 | 2:30pm - 5:30pm | 3 | DEV | Prototypying and intergration of detection of orientation, updating the main processing sketch
Eiren | Thursday | 2016-03-31 | 7:00pm - 8:15pm | 1.25 | DOC | Writing about page content and getting all attributions
Eiren | Thursday | 2016-03-31 | 12:00am - 1:15am | 1.25 | DEV | Intergate of about page content
Laura | Saturday | 2016-04-02 | 12:45pm - 2:45pm | 2 | DEV | Successfully sending image to server, and responding with text and/or url to image for downloading
Laura | Saturday | 2016-04-02 | 2:45pm - 4:00pm | 1.25 | DEV | Experimenting with ways to return the image in the HTTP response
Laura | Saturday | 2016-04-02 | 4:00pm - 6:15pm | 2.25 | DEV | Developing web server for green screen keying
Laura | Saturday | 2016-04-02 | 6:15pm - 8:00pm | 1.75 | DEV | Getting server running on Azure
Laura | Saturday | 2016-04-02 | 8:15pm - 9:30pm | 1.25 | DEV | Incorporating server keying requests into main app
Laura | Saturday | 2016-04-02 | 10:00pm - 1:45am | 3.75 | DEV | Trying to get http requests working in main app (libaries not two methods from http libraries)
Laura | Sunday | 2016-04-03 | 1:30pm - 7:00pm | 5.5 | DEV | Re-writing HTTP requests using core http libraries. Successfully running green screen server in main processing sketch. Unsure if it is running in main android app (as it keeps crashing due to lack of memory). Will test tomorrow
Laura | Sunday | 2016-04-03 | 7:45pm - 10:45pm | 3 | DEV | Trying to optimise app (Can't get to save share screen to add/test share options) - reduced memory load from 45MB to 19MB/30MB
Laura | Sunday | 2016-04-03 | 10:45pm - 11:45pm | 1 | LRN | Reinstalling Android Studio
Laura | Monday | 2016-04-04 | 1:00am - 2:00am | 1 | DEV | Getting image path version of main app running in Android Studio
Laura | Monday | 2016-04-04 | 9:00am - 11:00am | 2 | TST | Testing green screen keying on server, planning for this evening's meeting
Eiren | Monday | 2016-04-04 | 9:00am - 11:00am | 2 | TST | Testing green screen keying on server, planning for this evening's meeting
Laura | Monday | 2016-04-04 | 12:00pm - 1:30pm | 1.5 | DEV | Adding sharing options to main app. Adjusting icons on screens to accomodate for this. If a user does not save or share their image, they are redirected back to main app.
Eiren | Monday | 2016-04-04 | 12:00pm - 1:30pm | 1.5 | DOC | Change request form 4
Eiren | Monday | 2016-04-04 | 2:00pm - 9:15pm | 7.25 | DEV | Reviewed changed request form 4, doing app optimization, made adjustments to display and reviewed apps pages, wrote acceptance tests for current sprint, planned next sprint, released latest plat store version
Laura | Monday | 2016-04-04 | 2:00pm - 9:15pm | 7.25 | DEV | Reviewed changed request form 4, doing app optimization, made adjustments to display and reviewed apps pages, wrote acceptance tests for current sprint, planned next sprint, released latest plat store version
Total hours for Sprint-011 |  |  | 55
Sprint-012
Eiren | Tuesday | 2016-04-05 | 8:30am - 9:00am | 0.5 | GDN | Redone passport, globe and created a sharing icon
Laura | Tuesday | 2016-04-05 | 9:00am - 11:00am | 2 | DEV | Optimization on both mobile and tablet
Eiren | Tuesday | 2016-04-05 | 8:45am - 11:00am | 0.25 | GDN | Graphics
Eiren | Tuesday | 2016-04-05 | 8:45am - 11:00am | 2 | DEV | Optimization on both mobile and tablet
Eiren | Tuesday | 2016-04-05 | 11:00pm - 12:00am | 1 | DEV | Incorporation of new graphics and ability to return to camera live view
Eiren | Thursday | 2016-04-07 | 7:30am - 8:15am | 0.75 | DEV | Beginning of learning mode
Eiren | Thursday | 2016-04-07 | 1:45pm - 5:00pm | 3.25 | DEV | Optimization on both mobile and tablet, fixed scrolling/clicks
Laura | Thursday | 2016-04-07 | 1:45pm - 5:00pm | 3.25 | DEV | Optimization on both mobile and tablet, fixed scrolling/clicks
Eiren | Friday | 2016-04-08 | 7:30am - 9:30am | 2 | DEV | Learning Mode
Eiren | Friday | 2016-04-08 | 10:30am - 12:45pm | 2.25 | DEV | Learning Mode
Laura | Friday | 2016-04-08 | 1:45pm - 2:00pm | 0.25 | DOC | Re-doing questionairre on Google Play Store to get content rating
Laura | Friday | 2016-04-08 | 2:15pm - 9:45pm | 7.5 | DEV | on/off the saving and/or sharing of an individual image, SaveShareScreenA "next" button to a "done" button. default and switching of images for the save, twitter, shake movement, switching camera icon, learning mode and autosaveMode. Storing learning mode on/off setting in user preferences XML. ShareSaveUnsuccessfulScreen dynamic. Connection to the Twitter API only occurs if the user is logged in. try/catch mergeImages (send to unsuccessful screen). Current user's account name added to logout screen. Re-exported the larger graphics in the app. Trying to fix issue with the Twitter login button.
Eiren | Friday | 2016-04-08 | 4:00pm - 5:00pm | 1 | GDN | Re-creating twitter on/off, save on/off, shake on/off, switchview off button and resized all social media buttons,
Laura | Saturday | 2016-04-09 | 11:45am - 4:30pm | 4.75 | DEV | Recommenting code in main app, removed rectBackground variables from Rectangle class
Laura | Saturday | 2016-04-09 | 5:15pm - 6:45pm | 1.5 | DEV | Recommenting code in main app, ternary operators to decide default icon images, removed all password code (no longer needed)
Laura | Saturday | 2016-04-10 | 12:45pm - 12:45am | 12 | DEV | Recommenting code in main app, removing unnecessary constructors, fix to scrolling (now inherited instead of copied), fixes to randomLocations (stored in XML as opposed to FavouritesScreen), simplified location data, showing new favourites first. All classes completed, apart from half of the Sketch class
Eiren | Sunday | 2016-04-10 | 8:00pm - 10:00pm | 2 | DEV | Learning Mode
Eiren | Monday | 2016-04-11 | 12:00am - 1:00am | 1 | DEV | Learning Mode
Eiren | Monday | 2016-04-11 | 1:00am - 2:30am | 1.5 | DOC | Readme file for team project on github
Eiren | Monday | 2016-04-11 | 7:45am - 8:45am | 1 | DEV | Trying to incorporate learning mode into main sketch, having trouble
Laura | Monday | 2016-04-11 | 9:00am - 11:00am | 2 | PLN | Reviewing progress with John, fixing issue with camera live view
Eiren | Monday | 2016-04-11 | 9:00am - 11:00am | 2 | PLN | Reviewing progress with John
Laura | Monday | 2016-04-11 | 2:15pm - 6:00pm | 3.75 | DEV | Integrating learning mode into main app, beginning work on rotating the Google Street View image based on the device's orientation
Eiren | Monday | 2016-04-11 | 2:15pm - 6:00pm | 3.75 | DEV | Integrating learning mode into main app, beginning work on rotating the Google Street View image based on the device's orientation
Laura | Monday | 2016-04-11 | 7:15pm - 8:30pm | 1.25 | DEV | Working on alignment of background, keyed and overlay images, when saving an image as portrait/landscape, using either camera. Successfully saving out landscape and portrait images
Eiren | Monday | 2016-04-11 | 7:15pm - 8:30pm | 1.25 | DEV | Working on alignment of background, keyed and overlay images, when saving an image as portrait/landscape, using either camera. Successfully saving out landscape and portrait images
Laura | Monday | 2016-04-11 | 10:30pm - 3:15am | 4.75 | DEV | Recommenting code in main app
Laura | Tuesday | 2016-04-12 | 9:00am - 11:00am | 2 | PLN | Moving favourites and user preferences XML file to GitHub.io so they can be updated remotely, attributing ourselves, hiding Twitter icons from settings screen (if user has not yet logged in), planning for sprint-013
Eiren | Tuesday | 2016-04-12 | 9:00am - 11:00am | 2 | PLN | Moving favourites and user preferences XML file to GitHub.io so they can be updated remotely, attributing ourselves, hiding Twitter icons from settings screen (if user has not yet logged in), planning for sprint-013
Laura | Tuesday | 2016-04-12 | 12:15pm - 12:45pm | 0.5 | DEV | Compiling and releasing the first Production version of the app to the Google Play Store
Eiren | Tuesday | 2016-04-12 | 12:15pm - 12:45pm | 0.5 | DEV | Compiling and releasing the first Production version of the app to the Google Play Store
Total hours for Sprint-012 |  |  | 73.5
Sprint-013
Laura | Tuesday | 2016-04-12 | 4:30pm - 5:00pm | 0.5 | TST | Testing on Cole's Samsung S7 Edge
Eiren | Tuesday | 2016-04-12 | 4:30pm - 5:00pm | 0.5 | TST | Testing on Cole's Samsung S7 Edge
Laura | Thursday | 2016-04-14 | 12:30pm - 1:00pm | 0.5 | TST | Testing on Stuart's phone
Eiren | Thursday | 2016-04-14 | 12:30pm - 1:00pm | 0.5 | TST | Testing on Stuart's phone
Laura | Thursday | 2016-04-14 | 2:00pm - 2:30pm | 0.5 | DEV | Working on gettting background panning working in landscape mode
Eiren | Thursday | 2016-04-14 | 3:30pm - 6:45pm | 3.25 | DEV | Testing on Steves and Stuarts phone again, developed permissions request, tested on coles phone, learned about the different permissions and why its needed for our code. Permission for camera and storage
Eiren | Thursday | 2016-04-14 | 6:45pm - 8:15pm | 1.5 | TST | Testing on Steves and Stuarts phone again, developed permissions request, tested on coles phone, learned about the different permissions and why its needed for our code. Permission for camera and storage
Laura | Thursday | 2016-04-14 | 3:30pm - 6:00pm | 2.5 | DEV | Successfully got panning working in landscape mode, tried to fix flipping of camera image (not successful)
Laura | Friday | 2016-04-15 | 12:45pm - 1:30pm | 0.75 | DOC | Adding all releases to GitHub
Eiren | Friday | 2016-04-15 | 2:00pm - 5:30pm | 3.5 | DOC | Reading main apps comments
Laura | Friday | 2016-04-15 | 3:00pm - 4:30pm | 1.5 | DOC | Adding all releases to GitHub
Laura | Friday | 2016-04-15 | 4:45pm - 6:45pm | 2 | DEV | Ability to saveTwitter account
Laura | Friday | 2016-04-15 | 6:45pm - 7:15pm | 0.5 | DEV | Ability to log out of Twitter account
Eiren | Friday | 2016-04-15 | 7:00pm - 8:00pm | 1 | DOC | Reading main apps comments
Laura | Friday | 2016-04-15 | 7:15pm - 7:30pm | 0.25 | DEV | Minor fixes - click to hide loading screen as well as let it fade, adding code to allow user to go from settings screen to twitter login (commented out as fails due to out of memory errors)
Laura | Friday | 2016-04-15 | 10:45pm - 11:45pm | 1 | DEV | Recommenting app (CameraLiveViewScreen - google image panning), main Sketch class, TwitterLoginActivity_CheckLogin class (fix to reset Twitter icon on SaveShareScreenA if user logs out during session)
Eiren | Saturday | 2016-04-16 | 4:00pm - 4:30pm | 0.5 | DOC | Reading main apps comments
Laura | Saturday | 2016-04-17 | 5:45pm - 8:00pm | 2.25 | DOC | Reviewing and updating README file on main GitHub repository. Creating README files for resources repository and green screen keying server repository
Eiren | Saturday | 2016-04-16 | 10:30pm - 11:00pm | 1 | DEV | Adding in missing line, wont work
Laura | Saturday | 2016-04-16 | 9:30pm - 10:15pm | 0.75 | DEV | Creating front end interface for green screen server
Eiren | Saturday | 2016-04-16 | 10:15pm - 11:00pm | 0.75 | PLN | Call with Laura (re: white screen when app loads), fixing white screen
Laura | Saturday | 2016-04-16 | 10:15pm - 11:00pm | 0.75 | PLN | Call with Eiren (re: white screen when app loads), fixing white screen
Laura | Saturday | 2016-04-16 | 11:00pm - 11:30pm | 0.5 | DEV | Creating front end interface for green screen server
Eiren | Saturday | 2016-04-16 | 11:30pm - 11:45pm | 0.25 | PLN | Call with Laura (re: white screen when app loads)
Laura | Saturday | 2016-04-16 | 11:30pm - 11:45pm | 0.25 | PLN | Call with Eiren (re: white screen when app loads)
Eiren | Saturday | 2016-04-16 | 11:45pm - 12:30am | 0.75 | DOC | Doing google screenshots for mobile and tablet and writing store listings
Laura | Saturday | 2016-04-16 | 11:45pm - 1:15am | 1.5 | DOC | Creating class structure diagram
Eiren | Sunday | 2016-04-17 | 12:30am - 2:00am | 1.5 | DEV | twitter background image and scaling
Eiren | Sunday | 2016-04-17 | 3:00pm - 6.30pm | 3.5 | DEV | twitter background image and scaling
Eiren | Monday | 2016-04-18 | 7:45am - 11:00am | 3.25 | DEV | twitter background image now working. Have to apply to latest version on github, testing on different devices
Laura | Monday | 2016-04-18 | 9:00am - 11:00am | 2 | DEV | Adding onStop() event, fixing back button issue, fixing saving of user preferences (due to issue with add to favourites triggering learning mode)
Eiren | Monday | 2016-04-18 | 11:15am - 11:45am | 0.5 | DEV | Intergrating twitter scaling and twitter background into main app
Laura | Monday | 2016-04-18 | 11:00am - 11:45am | 0.75 | DOC | Updating and closing issues on GitHub
Eiren | Monday | 2016-04-18 | 1:00pm - 1:45pm | 0.75 | DEV | Finshed the intergrating twitter scaling and twitter background into main app, resolving issue on github
Laura | Monday | 2016-04-18 | 2:45pm - 5:30pm | 2.75 | DEV | Fix to background panning, testing app with multiple logins, increased memory heap, detecting if no internet available (toast)
Eiren | Monday | 2016-04-18 | 2:45pm - 5:30pm | 2.75 | DEV | Compliling Sprint 013 Production 3 release, Releasing on github
Total hours for Sprint-013 |  |  | 47.25
Sprint-014
Laura | Monday | 2016-04-18 | 5:30pm - 7:15pm | 2.25 | TST | Creating survery for user testing feedback
Eiren | Monday | 2016-04-18 | 5:30pm - 8:45pm | 3.25 | GDN | reviewed survey, created/updated the gradable project, re-exported switchViewIconImage
Laura | Monday | 2016-04-18 | 7:15pm - 9:15pm | 2 | DEV | Trying to detect if internet is available or not (AlertDialog, Toast)
Laura | Monday | 2016-04-18 | 11:45pm - 1:30am | 1.75 | DEV | Displaying pop up if no internet available, or if not enough green detected in the users environment
Eiren | Tuesday | 2016-04-18 | 8:30am - 11:30am | 3 | DEV | Testing toast pop ups, trying to rotate popups, discussing learning mode, fix to new learning mode (no longer turns off when clicks occur), testing app with John
Laura | Tuesday | 2016-04-18 | 8:30am - 11:30am | 3 | DEV | Testing toast pop ups, trying to rotate popups, discussing learning mode, fix to new learning mode (no longer turns off when clicks occur), testing app with John
Laura | Tuesday | 2016-04-18 | 12:30pm - 12:45pm | 0.25 | DEV | Releasing Sprint-013-Production-22 to Google Play store
Laura | Wednesday | 2016-04-20 | 1:00pm - 2:00pm | 1 | DEV | Trying to fix issue with Google Nexus 7 - telephony, internet etc. Not working
Eiren | Wednesday | 2016-04-20 | 1:00pm - 2:00pm | 1 | DEV | Trying to fix issue with Google Nexus 7 - telephony, internet etc. Not working
Eiren | Thursday | 2016-04-21 | 2:15pm - 5:30pm | 3.25 | DEV | Input comments for permissions, researching problems related to why the nexus 7 is not able to download app, uploaded new google play images
Laura | Thursday | 2016-04-21 | 2:15pm - 5:30pm | 3.25 | DEV | Researching problems related to why the nexus 7 is not able to download app, testing different ways for the nexus, fixing naming convention of images, adding rotation to icons on image preview screen
Total hours for Sprint-014 |  |  | 24
|  |  | Total Hours Overall | 835.75